## Instructions
SPRINT DASHBOARD TEMPLATE
HOW TO USE THIS TEMPLATE
1. SPRINT SETUP | Go to the 'Sprint Setup' sheet and enter your sprint details:
• Sprint name, start/end dates, team size
• Team member names, roles, daily capacity, days off
• Sprint goal and total committed story points
2. DAILY BURNDOWN | Each day of the sprint, enter:
• Remaining story points (auto-calculates from Sprint Backlog)
• Scope changes (added or removed story points)
• Blockers count and cumulative blocker hours
The burndown chart updates automatically.
3. SPRINT BACKLOG | List all stories/tasks for the sprint:
• Story ID, Title, Assignee, Story Points, Status
• Start Date, End Date (for cycle time calculation)
• Type: New Feature / Tech Debt / Bug / Compliance
• Escaped Defect flag (Yes/No)
4. BLOCKER TRACKER | Log every blocker and impediment:
• Blocker ID, Description, Raised Date, Resolved Date
• Owner, Status, Aging (auto-calculated in hours)
• Impact: Critical / High / Medium / Low
5. VELOCITY TRACKER | Track velocity across sprints:
• Enter completed story points per sprint
• Rolling average auto-calculates for 3-sprint and 6-sprint windows
• Velocity trend chart updates automatically
6. COMPLIANCE & AUDIT | For healthcare IT (HIPAA) and financial IT (SOX) teams:
• Control test pass rate per sprint
• Access review completion percentage
• Audit trail coverage (system changes with complete logs)
• Remediation velocity (compliance vs. innovation split)
7. KPI SUMMARY | Auto-calculated metrics at a glance:
• Sprint Predictability Score
• Flow Efficiency
• Scope Change Percentage
• Escaped Defect Rate
• Blocker Resolution Time (average hours)
• Tech Debt Ratio
FORMULAS REFERENCE
Metric | Formula | Location
Remaining Story Points |  | Daily Burndown
Scope Change % |  | KPI Summary
Flow Efficiency |  | KPI Summary
Sprint Predictability |  | KPI Summary
Blocker Aging (hours) |  | Blocker Tracker
Rolling Avg Velocity (3) |  | Velocity Tracker
Tech Debt Ratio |  | KPI Summary
COLOR CODING LEGEND
Green | On track / Healthy / Passing
Yellow | At risk / Warning / Needs attention
Red | Blocked / Failing / Critical
Blue | Headers / Information
NOTES
• Do not delete formula cells. They auto-calculate from input data.
• All dates should be entered in MM/DD/YYYY format.
• Story points should be whole numbers (Fibonacci: 1,2,3,5,8,13,21).
• For SAFe teams: Use the 'Program Dashboard' sheet for PI-level tracking.
• For compliance teams: Fill the 'Compliance & Audit' sheet each sprint.

## Sprint Setup
SPRINT SETUP
Sprint Name | Sprint 24 |  | Sprint Start Date | 05/01/2026
Sprint Number | 24 |  | Sprint End Date | 05/14/2026
Sprint Goal | Complete HL7 FHIR integration module and pass HIPAA compliance audit
Total Sprint Days |  |  | Working Days | 10
COMMITTED SCOPE
Total Committed Story Points | 55
Number of Stories | 8
Number of Bugs | 3
Number of Tech Debt Items | 2
TEAM CAPACITY
Team Member | Role | Daily Capacity (hrs) | Days Off | Available Hours | Activity
Sarah Chen | Scrum Master | 6 | 1 |  | Scrum Master
Marcus Johnson | Tech Lead | 6 | 0 |  | Development
Priya Patel | Senior Dev | 6 | 2 |  | Development
David Kim | QA Engineer | 6 | 0 |  | Testing
Lisa Rodriguez | BA / Product Owner | 4 | 1 |  | Business Analysis
James Wilson | DevOps Engineer | 6 | 0 |  | DevOps
TOTAL TEAM CAPACITY |  |  |  |  | hours
SPRINT HEALTH THRESHOLDS
Metric | Green (Healthy) | Yellow (At Risk) | Red (Critical) | Current | Status
Scope Change % | < 10% | 10-15% | > 15% | 0%
Blocker Resolution (hrs) | < 24 | 24-48 | > 48 | 0
Sprint Predictability | > 90% | 80-90% | < 80% | 100%
Escaped Defects | 0 | 1-2 | > 2 | 0
Flow Efficiency | > 40% | 25-40% | < 25% | 0%

## Daily Burndown
Day | Date | Ideal Remaining | Actual Remaining | Scope Change (+/-) | Cumulative Blockers | Blocker Hours | Notes
1 | 05/01/2026 | 55 | 55 | 0 | 0 | 0 | Sprint kickoff
2 | 05/02/2026 |  | 52 | 0 | 1 | 4 | HL7 FHIR API blocker identified
3 | 05/03/2026 |  | 48 | 0 | 1 | 4
4 | 05/04/2026 |  | 42 | 3 | 2 | 12 | Scope added: HIPAA audit logging
5 | 05/05/2026 |  | 36 | 0 | 1 | 8 | Blocker resolved
6 | 05/06/2026 |  | 30 | 0 | 0 | 0
7 | 05/07/2026 |  | 24 | 0 | 1 | 6 | Database migration delay
8 | 05/08/2026 |  | 18 | 0 | 0 | 0
9 | 05/09/2026 |  | 12 | -2 | 0 | 0 | Scope removed: duplicate story
10 | 05/10/2026 |  | 6 | 0 | 0 | 0
11 | 05/11/2026 |  | 2 | 0 | 0 | 0 | Final testing
12 | 05/12/2026 |  | 0 | 0 | 0 | 0 | Sprint complete

## Sprint Backlog
Story ID | Title | Assignee | Story Points | Status | Start Date | End Date | Type | Priority | Escaped Defect | Cycle Time (days)
HEALTH-101 | Implement HL7 FHIR Patient Resource API | Marcus Johnson | 13 | Done | 05/01/2026 | 05/06/2026 | New Feature | High | No
HEALTH-102 | Add HIPAA audit logging to all data access | Priya Patel | 8 | Done | 05/02/2026 | 05/07/2026 | Compliance | Critical | No
HEALTH-103 | Refactor legacy authentication module | Marcus Johnson | 5 | In Progress | 05/04/2026 |  | Tech Debt | Medium | No
HEALTH-104 | Fix Epic EHR integration timeout bug | David Kim | 5 | Done | 05/01/2026 | 05/03/2026 | Bug | High | No
HEALTH-105 | Create SOX control test automation | James Wilson | 8 | Done | 05/03/2026 | 05/08/2026 | Compliance | Critical | No
HEALTH-106 | Update user access review workflow | Lisa Rodriguez | 3 | Done | 05/01/2026 | 05/02/2026 | Compliance | Medium | No
HEALTH-107 | Implement OAuth2 token refresh logic | Priya Patel | 5 | In Progress | 05/05/2026 |  | New Feature | High | No
HEALTH-108 | Database schema migration for audit tables | James Wilson | 5 | Done | 05/02/2026 | 05/05/2026 | New Feature | Medium | No
HEALTH-109 | Fix pagination bug in provider search | David Kim | 3 | Done | 05/04/2026 | 05/05/2026 | Bug | Low | Yes
HEALTH-110 | Add input validation for FHIR bundles | Priya Patel | 3 | To Do |  |  | New Feature | Medium | No
HEALTH-111 | Document API endpoints for security audit | Lisa Rodriguez | 2 | Done | 05/06/2026 | 05/07/2026 | Compliance | Medium | No
HEALTH-112 | Optimize SQL queries for patient lookup | Marcus Johnson | 3 | To Do |  |  | Tech Debt | Low | No
HEALTH-113 | Configure CI/CD pipeline for compliance checks | James Wilson | 5 | Done | 05/01/2026 | 05/04/2026 | DevOps | High | No
Formulas:
Cycle Time (days) = IF([End Date]="",TODAY()-[Start Date]+1,[End Date]-[Start Date]+1)

## Blocker Tracker
Blocker ID | Description | Raised Date | Resolved Date | Owner | Status | Aging (hrs) | Impact | Root Cause | Resolution
BLK-001 | HL7 FHIR API endpoint returning 500 errors | 05/02/2026 09:00 | 05/02/2026 13:00 | James Wilson | Resolved |  | Critical | Missing SSL certificate config | Updated nginx proxy settings
BLK-002 | Epic EHR sandbox environment down | 05/04/2026 11:00 | 05/05/2026 09:00 | David Kim | Resolved |  | High | Vendor maintenance window | Coordinated with Epic support
BLK-003 | Database migration script failing on staging | 05/07/2026 14:00 |  | James Wilson | Open |  | High | Foreign key constraint violation | In progress - refactoring script
BLK-004 | SOX auditor requesting additional access logs | 05/05/2026 10:00 | 05/05/2026 16:00 | Lisa Rodriguez | Resolved |  | Medium | Audit scope expansion | Exported logs from SIEM
BLK-005 | Code review bottleneck - 3 stories pending | 05/08/2026 09:00 | 05/08/2026 15:00 | Marcus Johnson | Resolved |  | Medium | Tech lead on PTO | Distributed review to senior devs

## Velocity Tracker
Sprint | Sprint Name | Committed Points | Completed Points | Incomplete Points | Late Completion | Predictability % | Rolling Avg (3) | Rolling Avg (6)
Sprint 19 | Sprint 19 - Foundation | 40 | 38 | 2 | 0
Sprint 20 | Sprint 20 - Core Features | 48 | 45 | 3 | 0
Sprint 21 | Sprint 21 - Integration | 52 | 50 | 2 | 0
Sprint 22 | Sprint 22 - Security Hardening | 45 | 42 | 3 | 0
Sprint 23 | Sprint 23 - Compliance Prep | 50 | 48 | 2 | 0
Sprint 24 | Sprint 24 - FHIR + HIPAA | 55 | 53 | 2 | 0
Sprint 25 | Sprint 25 - (Current) | 58

## Compliance & Audit
Sprint | Control Test Pass Rate % | Access Review Completion % | Audit Trail Coverage % | Remediation Points | Innovation Points | Compliance/Innovation Ratio | HIPAA Findings | SOX Findings | Audit Status
Sprint 21 | 92 | 100 | 85 | 15 | 35 |  | 1 | 0 | Pass
Sprint 22 | 95 | 100 | 90 | 20 | 25 |  | 0 | 0 | Pass
Sprint 23 | 98 | 100 | 95 | 25 | 23 |  | 0 | 1 | Pass
Sprint 24 | 96 | 100 | 98 | 20 | 33 |  | 0 | 0 | Pass
Sprint 25

## KPI Summary
SPRINT KPI DASHBOARD
METRIC | FORMULA | TARGET | ACTUAL | VARIANCE | STATUS
Sprint Predictability |  | > 90%
Scope Change % |  | < 10%
Flow Efficiency |  | > 40%
Blocker Resolution (hrs) |  | < 24
Escaped Defect Rate |  | 0%
Tech Debt Ratio |  | < 30%
Velocity Trend |  | Stable
Compliance Pass Rate |  | > 95%
OVERALL SPRINT HEALTH
Healthy Metrics
At Risk Metrics
Critical Metrics
OVERALL STATUS

## Program Dashboard (SAFe)
PI | Feature ID | Feature Name | Team | Committed SP | Completed SP | Status | Dependencies | Dependency Status | Risk Level | ROAM Status
PI 6.3 | FEAT-201 | Epic EHR Provider Dashboard | Team Alpha | 120 | 115 | On Track | FEAT-205 (Data Layer) | Resolved | Medium | Resolved
PI 6.3 | FEAT-202 | HL7 FHIR R4 Migration | Team Beta | 80 | 75 | On Track | FEAT-201 (API Contract) | In Progress | High | Owned
PI 6.3 | FEAT-203 | HIPAA Audit Automation | Team Gamma | 60 | 45 | At Risk | FEAT-202 (Auth Layer) | Blocked | Critical | Mitigated
PI 6.3 | FEAT-204 | SOX Control Testing Framework | Team Delta | 100 | 98 | On Track | None | N/A | Low | Resolved
PI 6.3 | FEAT-205 | Unified Data Layer | Team Alpha | 90 | 60 | At Risk | FEAT-203 (Schema) | In Progress | High | Owned
PI 6.4 | FEAT-301 | AI-Powered Clinical Decision Support | Team Alpha | 150 |  | Planned | FEAT-201, FEAT-205 | Requested | High | Accepted

## Retrospective
SPRINT RETROSPECTIVE
Sprint: | Sprint 24 |  | Date: | 05/14/2026
WHAT WENT WELL
1. HL7 FHIR integration completed ahead of schedule
2. HIPAA audit logging passed first review
3. Team maintained >40% flow efficiency
WHAT NEEDS IMPROVEMENT
1. Database migration script caused 6-hour blocker
2. One escaped defect in provider search pagination
3. Scope change of 3 points mid-sprint (HIPAA logging)
ACTION ITEMS | Owner | Target Sprint | Status | Priority
Add database migration validation to CI pipeline | James Wilson | Sprint 25 | To Do | High
Implement automated pagination testing for all APIs | David Kim | Sprint 25 | To Do | High
Enforce scope freeze after day 3 of sprint | Sarah Chen | Sprint 25 | To Do | Medium
Create runbook for Epic EHR sandbox recovery | David Kim | Sprint 25 | To Do | Medium
METRICS REVIEW
Metric | Previous Sprint | Current Sprint | Trend | Target
Velocity | 48 | 53 | ↑ +5 | Stable
Predictability | 96 | 96 | → Stable | > 90%
Scope Change % | 5 | 5.5 | → Stable | < 10%
Blocker Resolution (hrs) | 8 | 6.4 | ↓ Improved | < 24
Flow Efficiency | 38 | 42 | ↑ +4 | > 40%
Escaped Defects | 0 | 1 | ↑ +1 | 0
Tech Debt Ratio | 22 | 18 | ↓ Improved | < 30%