## Read Me
Healthcare Scrum Team Operating Kit
Companion to the TechFitFlow article: Scrum Team Roles in Healthcare IT
Tab | Purpose | How to use
Team Roster | Each person's Scrum role, home team, line manager, allocation | Fill yellow cells. Manager count and partial-allocation count calculate automatically.
Capacity Planner | Focus days per person after PTO, allocation and support buffer | Enter sprint length once (C4). Edit yellow cells. Focus days and team totals calculate.
Sprint Calendar | Fixed dates for events, config migrations, BAT windows | Enter Sprint 1 start date (B4). All dates roll forward automatically.
DoR-DoD | Definition of Ready and Done checklists for a mixed team | Edit items to match your team. Mark each Yes / No per story if useful.
BAT Sign-Off Record | Release-level business acceptance record for CAB | One record per release. Pass rate and readiness calculate.
Retro Actions | Action tracker that flags items needing a line manager | Log actions after each retro. Open-escalation count updates automatically.
Working Agreement | One-page two-manager agreement to sign before Sprint 1 | Replace sample text; collect signatures from each line manager, PO and SM.
Legend | Yellow fill = cells you edit | Grey fill = formulas. Example rows show expected format; overwrite them.

## Team Roster
Team Roster and Matrix Reporting
Scrum team role vs home team. One row per person.
Name | Org title | Scrum accountability | Home team | Line manager | Allocation % | Writes performance review | Gives review input | Backup / delegate
Dana | Product Owner | Product Owner | Digital Patient Experience | Director of Digital Health | 100% | Director of Digital Health | SM | Digital Health PO (other team)
Ray | Scrum Master | Scrum Master | Agile Delivery Office | Agile Delivery Manager | 100% | Agile Delivery Manager | PO | SM from sister team
Priya | Lab Informatics Specialist (BAT rep) | Developer | Laboratory Services | Lab Operations Director | 50% | Lab Operations Director | PO, SM | Lab supervisor (named)
Marcus | Quality Engineer | Developer | QE Practice | QE Manager | 100% | QE Manager | PO, SM | QE practice pool
Luis | EHR Configuration Analyst | Developer | Clinical Applications | Clinical Apps Manager | 60% | Clinical Apps Manager | PO, SM | Second results analyst
Anika | Integration Developer (Java) | Developer | Integration Engineering | Integration Eng Manager | 100% | Integration Eng Manager | PO, SM | Tom (paired)
Tom | Software Engineer (.NET) | Developer | Digital Engineering | Digital Eng Manager | 100% | Digital Eng Manager | PO, SM | Mei (paired)
Mei | Front-end Engineer (React) | Developer | Digital Engineering | Digital Eng Manager | 100% | Digital Eng Manager | PO, SM | Tom (paired)
Sam | Data Engineer (SQL) | Developer | Data & Analytics | Data & Analytics Manager | 100% | Data & Analytics Manager | PO, SM | Anika (paired)
Team size | 9
Distinct line managers | 8
Partially allocated people | 2
Total FTE on team | 8.1

## Capacity Planner
Sprint Capacity Planner
Focus days = (Sprint days - PTO) x Allocation - Support buffer
| Sprint working days | 10
| Ceremony overhead % | 10% | Share of time in Scrum events (planning, daily, refinement, review, retro). Assumption; adjust.
Name | Role | PTO / holiday days | Allocation % | Support buffer (days) | Focus days | Net of ceremonies | Points capacity (optional)
Priya | BAT rep | 0 | 50% | 0 | 5 | 4.5
Luis | Config analyst | 1 | 60% | 1 | 4.4 | 3.96
Marcus | QE | 0 | 100% | 0 | 10 | 9
Anika | Java dev | 0 | 100% | 1.5 | 8.5 | 7.65
Tom | .NET dev | 0 | 100% | 0.5 | 9.5 | 8.55
Mei | React dev | 0 | 100% | 0.5 | 9.5 | 8.55
Sam | SQL dev | 0 | 100% | 0.5 | 9.5 | 8.55
|  |  |  | Team focus days | 56.4 | 50.76
Bottleneck check
Config focus days | 3.96
Stories needing config | 4
Config days per story | 0.99
BAT focus days | 4.5
Stories needing BAT | 4
BAT days per story | 1.125
Flag | Bottleneck: cut config/BAT stories
Threshold of 1 day per story is an assumption; adjust to your history.

## Sprint Calendar
Two-Week Sprint Calendar
Enter Sprint 1 start date in B4. Day offsets are working days.
Sprint 1 start | 2026-10-07
Sprint number | 1 | Change to see dates for any sprint
Working day # | Event / milestone | Length | Required roles | Date
1 | Sprint Planning | 3 h | Whole team | 2026-10-07
1 | Daily Scrum starts (9:15 every day) | 15 min | Developers; PO/SM as needed | 2026-10-07
2 | Config migration to test (window 1) | Window | Config analyst | 2026-10-08
4 | Backlog refinement #1 | 60 min | PO, BAT, Config, QE, one dev per stack | 2026-10-12
6 | BAT validation window opens | Half-days | BAT rep, QE | 2026-10-14
7 | Config migration to test (window 2) | Window | Config analyst | 2026-10-15
8 | Backlog refinement #2 | 60 min | PO, BAT, Config, QE, one dev per stack | 2026-10-16
9 | BAT validation window closes | - | BAT rep | 2026-10-19
10 | Sprint Review | 60 min | Whole team + stakeholders | 2026-10-20
10 | Sprint Retrospective | 90 min | Whole team (no line managers) | 2026-10-20
Formulas:
Date = WORKDAY(B4,(B5-1)*10+[Working day #]-1)

## DoR-DoD
Definition of Ready and Definition of Done
Team working agreement (DoR) and Scrum commitment (DoD). Edit to fit.
# | Definition of Ready item | Owner | Met? (story check)
1 | Acceptance criteria reviewed by BAT rep and QE | PO
2 | Policy reference attached if compliance-driven | PO
3 | Config needs flagged with target migration date | Config analyst
4 | Test data source identified and PHI-safe | QE
5 | Status variants considered (corrected, cancelled, preliminary) | BAT rep
6 | Dependencies on other teams named with owner | SM
# | Definition of Done item | Owner | Met? (story check)
1 | Code reviewed and merged; pipeline green | Developers
2 | Config migrated to test with change record | Config analyst
3 | Automated tests added for each acceptance criterion | QE
4 | BAT rep accepted story in test (if bat-required) | BAT rep
5 | Audit logging verified for PHI access | QE
6 | Release notes drafted for service desk | PO
| Story ready? (all DoR = Yes) |  | Not ready
| Story done? (all DoD = Yes) |  | Not done

## BAT Sign-Off Record
BAT Sign-Off Record
One record per production release. Attach to the change request for CAB.
Release | 2026.11
Stories in scope | RR-214, RR-219, RR-224, RR-230, RR-247
Business rules / policy validated | HIM-POL-112 v3 sections 2.1-2.4; corrected-result handling
Evidence location | Confluence BAT page; query outputs; masked screenshots
Open defects and disposition | RR-249 Low, cosmetic, accepted for next release
Scenario ID | Scenario | Rule / AC | Result | Notes / evidence
BAT-01 | Genetic result held until clinician signs | AC-1, AC-2 | Pass | Query output 11/02
BAT-02 | Hold auto-releases at 72 hours | AC-2 | Pass
BAT-03 | Corrected genetic result (OBR-25 = C) follows hold rule | RR-247 | Pass | Retest after fix
BAT-04 | Mixed-panel ORU with genetic and routine results | RR-252 | Exception | Deferred; signed by Lab Ops Director
Scenarios run | 4
Passed | 3
Failed | 0
Signed exceptions | 1
Pass rate (excl. exceptions) | 100%
Ready to sign? | Yes
Signatory | Name | Role | Date | Signature
BAT representative | Priya | Lab Informatics Specialist
Business owner |  | Lab Operations Director
Business owner delegate |  | Named in working agreement
Product Owner (acknowledgment) | Dana | Product Owner

## Retro Actions
Retrospective Action Tracker
Flag actions that need a line manager. SM escalates within two days.
Sprint | Action | Owner | Needs line manager? | Which manager | Due | Status | Age (days, auto) | Logged on (date) | Summary
14 | Add corrected and cancelled statuses to HL7 generator | Marcus | No |  | Sprint 15 | In progress | 2 | 2026-09-30 | Open actions | 2
14 | Add status-variant check to Definition of Ready | Priya + Dana | No |  | Next refinement | Done |  | 2026-09-30 | Open escalations to managers | 1
14 | Standing weekly config migration slot to test | Ray | Yes | Clinical Apps Manager | 2 weeks | Open | 2 | 2026-09-30 | Done | 2
14 | Raise Luis support buffer to 1.5 days in capacity plan | Ray | Yes | Clinical Apps Manager | Sprint 15 planning | Done |  | 2026-09-30
Formulas:
Age (days, auto) = IF(OR([Logged on (date)]="",[Status]="Done"),"",TODAY()-[Logged on (date)])

## Working Agreement
Two-Manager Working Agreement
Sign before Sprint 1. Review every Program Increment or quarter.
Topic | Agreement
Team and product | Results Release team; lab result delivery from LIS to EHR to patient portal
Sprint length and start day | Two weeks, starting Wednesday
Priorities | Product Owner orders the backlog. Line managers set allocation before Sprint Planning.
Allocation changes | Changed with at least 2 days' notice before planning; never mid-sprint except P1 incidents
Production support | Config analyst support buffer: 1.5 days per sprint. P1 incidents override; SM informed same day.
BAT representative time | 50% allocation; blocked BAT half-days on sprint days 6-9; delegate named for flu-season surge
BAT sign-off authority | BAT rep + Lab Operations Director; delegate: named lab supervisor
Performance input | PO and SM send written contribution summary to each line manager every PI / quarter
Retrospectives | Line managers do not attend. SM escalates manager-owned actions within 2 working days.
Standards | Home teams own coding, testing, build and data standards; Scrum team may propose changes
Escalation path | SM -> line manager -> Director of Digital Health
Signatory (role) | Name / signature / date
Product Owner
Scrum Master
Lab Operations Director
QE Manager
Clinical Apps Manager
Integration Eng Manager
Digital Eng Manager
Data & Analytics Manager

## Lookups
Lookups
Drop-down sources
Scrum accountability | Status | Yes/No | Result
Product Owner | Open | Yes | Pass
Scrum Master | In progress | No | Fail
Developer | Done |  | Exception
| Blocked |  | Not run