## Read Me
QA, QE & Business Acceptance Role Toolkit
Companion to the TechFitFlow article: QA vs QE vs Business Acceptance Tester
Tab | What it is for | How to use it
RACI Matrix | One owner (A) per quality activity across QA, QE, BAT, BA, PO, Dev | Edit R/A/C/I letters in yellow cells. Column H flags rows without exactly one A.
Entry-Exit Criteria | Gate conditions for QE pipeline, QA system testing, BAT and UAT | Replace sample criteria with your program's. Owner column = who enforces the gate.
Defect Routing Log | Classifies escaped defects by which role's gate should have caught them | Fill yellow columns. 'Should have caught' and 'Escaped?' calculate automatically. Summary at the right.
BAT Sign-Off Checklist | Evidence checklist before business acceptance sign-off | Set Status per item. Completion % updates automatically.
Role Gap Assessment | 15-statement self-check to find the weakest quality perspective | Score each statement 1-5. Lowest role average = where to invest first.
Lookups | Drop-down lists and routing map | Change only if your defect categories differ.
Legend | Yellow fill = cells you edit | White/grey cells = formulas or reference text
Note | Row 1 of each log contains an example of expected format | Overwrite or delete the example row when you start.

## RACI Matrix
Quality RACI Matrix
Exactly one A (or A/R) per row. Column H checks it.
Activity | QA | QE | BAT | BA | PO | Dev | One A? (check)
Acceptance criteria review | C | C | C | R | A | C | OK
Test strategy and test plan | A/R | C | C | C | I | I | OK
Automation framework | C | A/R | I | I | I | C | OK
CI/CD quality gates | I | A | I | I | I | R | OK
Smoke suite before QA handoff | C | A/R | I | I | I | R | OK
System and regression testing | A/R | R | I | I | I | C | OK
Test data management | C | A/R | C | C | I | C | OK
Business-rule validation | C | I | A/R | C | I | I | OK
End-to-end business process testing | C | I | A/R | C | I | I | OK
Compliance evidence pack | R | C | A | C | I | I | OK
Defect triage and priority | C | C | C | I | A | C | OK
UAT coordination | R | I | C | R | A | I | OK
Release go / no-go input | R | R | R | I | A | I | OK

## Entry-Exit Criteria
Entry and Exit Criteria by Role Gate
Sample criteria from regulated programs. Replace with yours.
Gate | Owner (A) | Entry criteria | Exit criteria | Evidence stored at | Status
QE pipeline gate | QE lead | Merge request opened; unit tests pass locally | Contract, API and smoke suites green; flaky tests quarantined with ticket | CI run history | In progress
QA system testing | QA lead | Build deployed; smoke passed; stories at Ready for QA | All planned cases executed; no open Critical; every High has an accepted plan | Test tool cycle report | Not started
Business acceptance (BAT) | BAT lead / sponsor | QA summary issued; BAT data loaded; testers trained | Every business rule passed or has signed exception; sponsor signs BAT report | Signed BAT report | Not started
UAT | Product Owner | BAT signed; known limitations briefed to users | User group lead and PO sign UAT completion | UAT sign-off | Not started
Release go / no-go | Release manager | All gate reports available | Decision recorded with open risks and rollback plan | Change record | Not started

## Defect Routing Log
Defect Routing Log
Which role's gate should have caught each defect? Fill yellow columns only.
Defect ID | Summary | Phase found | Detected by role | Defect category | Should have caught (auto) | Escaped? (auto) | Action / test added | Summary: should have been caught by
PAAPI-467 | Decision clock starts at assignment, not receipt | BAT | BAT | Requirement wrong or missing | BAT / BA | No | Rule added to BAT checklist; AC rewritten | Gate owner | All defects | Escaped to UAT/Prod
[8 empty] | BAT / BA | 1 | 0
[8 empty] | QE | 0 | 0
[8 empty] | QA | 0 | 0
[8 empty] | QE (environment) | 0 | 0
[8 empty] | UAT | 0 | 0
[8 empty] | Total | 1 | 0
[8 empty] | Weakest gate | BAT / BA
Row 5 is an example. Overwrite it with your first defect.

## BAT Sign-Off Checklist
Business Acceptance Sign-Off Checklist
Each item should point to stored evidence, not memory.
# | Checklist item | Status | Evidence link / location | Owner | Notes
1 | Every business rule ID in scope has a linked BAT scenario | Done | Jira filter: BAT-scope rules | BAT lead
2 | Each scenario shows pass, fail, or signed exception with owner and due date | Not started
3 | Calculation outputs reconciled against an independent source | Not started
4 | Compliance fields verified with the compliance analyst | Not started
5 | Test data source documented; PHI/PII masked per data-use approval | Not started
6 | Open defects reviewed with PO; no Critical; every High has workaround or fix date | Not started
7 | Downstream reports, extracts and interfaces checked for one full business cycle | Not started
8 | Feature-flag state at sign-off recorded (on / off) with follow-up sign-off if off | Not started
9 | Evidence stored where auditors expect it (screenshots, query output, signed report) | Not started
10 | UAT team briefed on known limitations | Not started
| Completion (Done / applicable items) | 10%
| Ready to sign? | Not yet

## Role Gap Assessment
Role Gap Self-Assessment
Score 1 (never true) to 5 (always true). Lowest average = invest there first.
# | Statement | Role perspective | Score (1-5) | Results
1 | Test cases use named techniques (boundary, decision table, state transition) | QA | 3 | Role | Average | Signal
2 | Every requirement traces to at least one executed test | QA | 3 | QA | 3 | Partial
3 | Defect reports are reproducible by a developer in under five minutes | QA | 3 | QE | 3 | Partial
4 | Regression scope is chosen by risk, not by habit | QA | 3 | BAT | 3 | Partial
5 | QA reviews acceptance criteria before sprint commitment | QA | 3 | Invest first in | QA
6 | A smoke suite runs automatically before any human tests a build | QE | 3
7 | Contract or API tests block merges when they fail | QE | 3 | Scores default to 3 as placeholders. Replace with your team's answers.
8 | Flaky tests are tracked and fixed within one sprint | QE | 3
9 | Test data can be created on demand without production copies | QE | 3
10 | Change failure rate is measured and reviewed each release | QE | 3
11 | A named business tester validates rules before UAT starts | BAT | 3
12 | Calculations are reconciled against an independent source | BAT | 3
13 | Compliance fields are verified with a compliance owner | BAT | 3
14 | Business testers have protected time on the release plan | BAT | 3
15 | Escaped business-rule defects are tracked per release | BAT | 3

## Lookups
Lookups
Drop-down sources and routing map
Defect category | Should have been caught by | Phase found | Status | RACI code | Role
Requirement wrong or missing | BAT / BA | QE pipeline | Done | A | QA
Business rule or calculation | BAT / BA | QA system test | In progress | R | QE
Compliance or regulatory field | BAT / BA | BAT | Not started | A/R | BAT
Schema or contract violation | QE | UAT | N/A | C | BA
Regression in existing feature | QE | Production |  | I | PO
Build or deployment failure | QE |  |  |  | Dev
Functional logic vs spec | QA
Boundary or state handling | QA
Environment or test data gap | QE (environment)
Usability or workflow fit | UAT